## Sheet1
| 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01
Annual Leave (or other time out of the office) | 2017-09-01: 4 to 7; 2017-10-01: 16 to 23
Academic year
CMALT and Professional Development
Update website re application process | 2017-06-01: 13
Advertise - mailing lists | 2017-06-01: 13
ALT people here to present | 2017-06-01: 20
Application submission deadline | 2017-07-01: 14
Application acceptance deadline | 2017-07-01: 28
Planning | 2017-07-01: July
Online course - planning - networking options? | bar: 2017-10-01
Online course - live
2 weekly virtual meeting (opt in)
Mailing list - via online course
Submission Dates | 2017-10-01: 30-Set; 2018-02-01: 2019-01-31; 2018-06-01: 2019-05-31
Cohort aiming to submit October 1st (defered from Year 1) | bar: 2017-06-01 to 2017-07-01; 2017-09-01 to 2017-11-01; 2018-01-01 to 2018-02-01; 2018-05-01 to 2018-06-01; 2018-09-01
Count down emails (course announcements) | 2017-08-01: 4, 18, 25; 2017-09-01: 1, 8, 15, 22
Meeting: Where are we? Planning to submit - F2F | 2017-08-01: Aug
Meeting: Progress and Questions - online | 2017-08-01: Aug
Meeting: Progress and Questions - online | 2017-09-01: Sept
Meeting: Peer review - F2F | 2017-09-01: Sept
Review portfolio | 2017-08-01: Aug; 2017-09-01: Sept
Writing Reteats | 2017-08-01: Aug; 2017-09-01: Sept
Celebration Event | 2017-11-01: Nov
Cohort aiming to submit February 1st | bar: 2017-06-01 to 2017-07-01; 2017-09-01 to 2017-11-01; 2018-01-01 to 2018-02-01; 2018-05-01 to 2018-06-01; 2018-09-01
Count down emails (course announcements) 12, 10, 8, 6, 5, 4, 3, 2, 1 | 2017-11-01: 9 , 23; 2017-12-01: 8, 21, (28); 2018-01-01: 4, 11, 18, 25
Meeting: Getting Started / Example Portfolio - F2F | 2017-09-01: Sept
Meeting: Core Areas 1 & 2 - F2F | 2017-09-01: Sept
Meeting: Core Area 3 & 4 - F2F | 2017-10-01: Oct
Webinar: Progress check (1 hour) | 2017-12-01: Dec
Meeting: Peer review - F2F | 2018-01-01: Jan
Writing Reteats | 2017-10-01: Oct; 2017-11-01: Nov; 2017-12-01: Dec
Cohort aiming to submit June 1st | bar: 2017-06-01 to 2017-07-01; 2017-09-01 to 2017-11-01; 2018-01-01 to 2018-02-01; 2018-05-01 to 2018-06-01; 2018-09-01
Count down emails (course announcements) 12, 10, 8, 6, 5, 4, 3, 2, 1 | 2018-03-01: 9, 23; 2018-04-01: 6, 20, 27; 2018-05-01: 4, 11, 18, 25
Meeting: Getting Started - F2F | 2018-02-01: Feb
Meeting: Core Area 1 & 2 - F2F | 2018-02-01: March
Meeting: Core Area 3 & 4 - F2F | 2018-03-01: March
Webinar: Progress check (1 hour) | 2018-04-01: April
Meeting: Peer review - F2F | 2018-05-01: May
Writing Reteats | 2018-02-01: Feb; 2018-03-01: March; 2018-04-01: April
Wider Community Events
Policy and Legislation | 2017-10-01: 2017-10-26
This work is licensed under a Creative Commons Attribution 4.0 International License.
© Susan Greig, University of Edinburgh 2019 CC BY